## Test Scenerios
Test Scenario Id | Test scenario description | Priority | Number of test cases
TS_001 | Validate the Register functionality | P1 | 10
TS_002 | Validate the Log-in functionality | P1 | 10
TS_003 | Validate the Log-out functionality | P1 | 10
TS_004 | Validate the product search functionality | P2 | 10
TS_005 | Validate the Category filter | P3 | 10
TS_006 | Validate the product page functionality | P2 | 10
TS_007 | Validate the Wishlist functionality | P4 | 10
TS_008 | Validate the Shopping Cart functionality | P4 | 10
TS_009 | Validate the Change Password functionality | P3 | 10
TS_010 | Validate Product reviews functionality | P5 | 10

## Register
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_REG_01 | TS_001 | Validate registration with valid data | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds 4)Click Submit | First Name: Shreya Last name: Kulal E-Mail: shreyakulal@gmail.com Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | Success message: Your Account Has Been Created! | Success message: Your Account Has Been Created! | P1 | Works good | Pass
TC_REG_02 | TS_001 | Registration with empty data and do not agree privacy policy | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Do not enter any fields. 4)Click Submit | NONE | Error message: Enter required fields. | Error message: You must agree to the Privacy Policy! | P1 | Works good but warning message should be changed | Pass
TC_REG_03 | TS_001 | Registration with invalid email format | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds and make invalid email format. 4)Click Submit | First Name: Shreya Last name: Kulal E-Mail: shreyakulal@hfghghfghg Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | Error message: E-Mail Address does not appear to be valid! | Error message: E-Mail Address does not appear to be valid! | P3 | Works good | Pass
TC_REG_04 | TS_001 | Registration with existing email address | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds with already registered email. 4)Click Submit | First Name: Shreya Last name: Kulal E-Mail: shreyakulal@gmail.com Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | Error message: E-Mail Address is already registered! | Error message: E-Mail Address is already registered! | P3 | Works good | Pass
TC_REG_05 | TS_001 | Registration with weak password | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds with weak password 4)Click Submit | First Name: Shreya Last name: Kulal E-Mail: shreyakulal@gmail.com Telephone: 686868686868 Password: hi Password Confirm: hi | Error message: Password must be between 4 and 20 characters! | Error message: Password must be between 4 and 20 characters! | P1 | Works but only checks length of password. | Pass
TC_REG_06 | TS_001 | Registration with password mismatch | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds and write different value in Password and Confirm password field. 4)Click Submit | First Name: Shreya Last name: Kulal E-Mail: shreya@gmail.com Telephone: 686868686868 Password: shreya Password Confirm: shreyaK | Error message: Password confirmation does not match password! | Error message: Password confirmation does not match password! | P1 | Works good | Pass
TC_REG_07 | TS_001 | Registration with leaving privacy policy check box | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds and do not select Newsletter which is optional. 4)Click Submit | First Name: Shreya Last name: Kulal E-Mail: shreyakulal@gmail.com Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | Success message: You must agree to the Privacy Policy! | Success message: You must agree to the Privacy Policy! | P3 | Works good | Pass
TC_REG_08 | TS_001 | Registration with special characters in name | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds with a special character in name 4)Click Submit | First Name: Shreya@ Last name: Kulal E-Mail: shreya@gmail.com Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | System should allow registration with special characters unless explicitly restricted. | Success message: Your Account Has Been Created! | P1 | Works good | Pass
TC_REG_09 | TS_001 | Registration with long name | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds with a long name 4)Click Submit | First Name: Shreya@kulal shreya shreya shreya kulal Last name: Kulal E-Mail: shreya@gmail.com Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | System may or may not allow registration depending on the specific character limit set for the name field. | Success message: Your Account Has Been Created! | P3 | Works good | Pass
TC_REG_10 | TS_001 | Registration with an email address containing uppercase characters | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Go to MyAccount-Click on Register 3)Enter the required fileds and enter email with upper case 4)Click Submit | First Name: Shreya@ Last name: Kulal E-Mail: SHREYA@gmail.com Telephone: 686868686868 Password: shreyaK Password Confirm: shreyaK | System should allow registration regardless of the case used in the email address | Success message: Your Account Has Been Created! | P1 | Works good | Pass

## Log-in
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_LI_01 | TS_002 | Login with valid credentials | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds with valid data 4)Click LOG IN | Email: shreya@gmail.com Password: aqaq | User should be successfully logged in and redirected to the homepage. | User is able to successfully log in and redirected to the homepage. | P1 | Works good | Pass
TC_LI_02 | TS_002 | Login with unregistered email | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds with an unregistered email 4)Click LOG IN | Email: kulal@gmail.com Password: aqaq | User should get an error message | Error message: No match for E-Mail Address and/or Password. | P1 | Works good | Pass
TC_LI_03 | TS_002 | Login with incorrect password | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds with incorrect password 4)Click LOG IN | Email: shreya@gmail.com Password: asas | Error message should be displayed of invalid password or fields | Error message: No match for E-Mail Address and/or Password. | P1 | Works good | Pass
TC_LI_04 | TS_002 | Login with empty email and password | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | NONE | User should get an error message to fill the fields. | Error message: No match for E-Mail Address and/or Password. | P2 | Works good bu warning message should be changed | Pass
TC_LI_05 | TS_002 | Login with empty email but valid password | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | Email: None Password: aqaq | User should get an error message to fill the fields. | Error message: No match for E-Mail Address and/or Password. | P1 | Works good bu warning message should be changed | Pass
TC_LI_06 | TS_002 | Login with valid email but empty password | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | Email: shreya@gmail.com Password: None | User should get an error message to fill the fields. | Error message: No match for E-Mail Address and/or Password. | P3 | Works good bu warning message should be changed | Pass
TC_LI_07 | TS_002 | Login with multiple consecutive incorrect password attempts | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | Email: shreya@gmail.com Password: random | User should get a warning regarding multiple attempts and should be redirected to forgot password page | After multiple attempts user is not getting any warning and is not redirected to forgot password page. | P3 | Not working | Failed
TC_LI_08 | TS_002 | Login with a leading or trailing space in the email address | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | Email: shreya@gmail.com Password: aqaq | User should be successfully logged in and redirected to the homepage. | User is able to successfully log in and redirected to the homepage. | P2 | Works good | Pass
TC_LI_09 | TS_002 | Login with an email address containing non-alphanumeric characters | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | Email: shreya@gmail.com Password: aqaq | User should be successfully logged in and redirected to the homepage. | User is able to successfully log in and redirected to the homepage. | P3 | Works good | Pass
TC_LI_10 | TS_002 | Validate forgot password functionality on click | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Click on Log in 3)Enter the required fileds 4)Click LOG IN | Email: shreya@gmail.com Password: aqaq | User should be redirected to forgot password page | User is getting redirected to forgot password page | P2 | Works good | Pass

## Log-out
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_LO_01 | TS_003 | Logout after successful login | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | User should be logged out and redirected to the home page | User is successfully logged out and redirected to homepage | P1 | Works good | Pass
TC_LO_02 | TS_003 | Logout from a specific account page | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | User should be logged out and redirected to the home page | User is successfully logged out and redirected to homepage | P1 | Works good | Pass
TC_LO_03 | TS_003 | Logout while leaving the browser window open | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Exit the webpage without clicking Log out | Email: kulal@gmail.com Password: aqaq | User should be logged out automatically | User is be logged out automatically | P2 | Works good | Pass
TC_LO_04 | TS_003 | Attempt to access an account page after logout | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Search for Account page | None | User will not find account page after log out. | User is not able to find account page after log out. | P2 | Works good | Pass
TC_LO_05 | TS_003 | Logout attempt from a different browser tab or window | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Duplicate the web page 3)Click on Log out from 2nd webpage | Email: kulal@gmail.com Password: aqaq | User should be logged out and redirected to the home page | User is successfully logged out and redirected to homepage | P3 | Works good | Pass
TC_LO_06 | TS_003 | Logout while having an active shopping cart | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | User should be logged out and redirected to the home page | User is successfully logged out and redirected to homepage | P2 | Works good | Pass
TC_LO_07 | TS_003 | Logout attempt during a network outage | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | logout will not be successful due to the network issue. | Log out is unsuccessful | P1 | Works good | Pass
TC_LO_08 | TS_003 | Logout attempt followed by immediate login attempt | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | User should be able to log in successfully again after a proper logout. | User is be able to log in successfully again after a proper logout. | P2 | Works good | Pass
TC_LO_09 | TS_003 | Logout attempt while processing an online order | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | User should be logged out and redirected to the home page | User is successfully logged out and redirected to homepage | P3 | Works good | Pass
TC_LO_10 | TS_003 | Logout attempt using a browser in incognito or private browsing mode | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Register / Log in 3)Click on Log out | Email: kulal@gmail.com Password: aqaq | Logging out from a private browsing window should clear the session data associated with that specific window | User is successfully logged out | P3 | Works good | Pass

## Search
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_SE_01 | TS_004 | Search by product name | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter text in search field 3)Click Search button | Search: Mac Book | The search results page should display the product | The search results page displayed the product | P1 | Works good | Pass
TC_SE_02 | TS_004 | Search by partial product name | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter a partial name or keyword related to a product 3)Click Search button | Search: Mac | The search results page should display a list of products containing the keyword in their names, descriptions, or related categories. | The search results page is successfully displaying a list of products containing the keyword in their names, descriptions, or related categories. | P3 | Works good | Pass
TC_SE_03 | TS_004 | Search using a misspelling of a product name | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter a misspelling of a product name 3)Click Search button | Search: ifhone | The system might offer suggestions for correcting | The system is not offer suggestions for correcting | P3 | Does not search | Failed
TC_SE_04 | TS_004 | Search using a product category | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2) Select a product category from the available options 3)Click Search button | Search: pc | The search results page should display products belonging to the chosen category. | The search results page should display products belonging to the chosen category. | P3 | Works good | Pass
TC_SE_05 | TS_004 | Search using a combination of keywords | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter multiple keywords separated by spaces in search field 3)Click Search button | Search: mac | The search results should refine the list based on all the keywords used | No products were found that matched your criteria. | P3 | Does not work | Failed
TC_SE_06 | TS_004 | Search by product brand | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter the name of a specific brand associated with products on the site in Search field. 3)Click Search button | Search: mac | The search results should display products belonging to the chosen brand | The search results is not displaying products belonging to the chosen brand | P2 | Does not search | Failed
TC_SE_07 | TS_004 | Search with no results | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter text in search field 3)Click Search button | NONE | The system should display a message indicating no results found | No products were found that matched your criteria. | P3 | Works good | Pass
TC_SE_08 | TS_004 | Search using advanced search filters | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Utilize the available advanced search filters to narrow down product results 3)Click Search button | Search: computer | The search results should be filtered according to the chosen criteria | Products are visible | P3 | Works good | Pass
TC_SE_09 | TS_004 | Search results sorting and pagination | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Enter text in search field 3)Perform a product search and observe the sorting options available 4)Click Search button | Search: MAC | Search results should be sortable based on offered criteria | Products are visible based on offered criteria | P2 | Works good | Pass
TC_SE_10 | TS_004 | Search term suggestions | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Start typing a product name or keyword in the search bar and observe if the system suggests potential matches 3)Click Search button | Search: pc | Search suggestions list should appear | Search suggestions list is appeared | P3 | Works good | Pass

## Category filter
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_CAT_01 | TS_005 | Verify Default Category Selection | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. | NONE | The default selected category should be "All Categories" | The default selected category is "All Categories" | P3 | Works good | Pass
TC_CAT_02 | TS_005 | Verify Category List Population | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. | NONE | All categories such as "Computers", "Electronics", "Apparel", etc., should be listed | All categories are listed | P3 | Works good | Pass
TC_CAT_03 | TS_005 | Verify Category Selection Functionality | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a specific category (e.g., "Books") | NONE | Only products from the selected category should be displayed | Only products from the selected category is displayed | P3 | Works good | Pass
TC_CAT_04 | TS_005 | Verify Subcategory Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a category with subcategories | NONE | Subcategories should be displayed under the main category |  | P3 | Works good | Pass
TC_CAT_05 | TS_005 | Verify No Products Message | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a category with no products | NONE | A message like "No products found" should be displayed. | No products were found that matched your criteria. | P3 | Works good | Pass
TC_CAT_06 | TS_005 | Verify Category Filter Reset | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select any category 5)Reset the filter to "All Categories" | NONE | All products should be displayed after resetting the filter | All products are displayed after resetting the filter | P3 | Works good | Pass
TC_CAT_07 | TS_005 | Verify URL Parameter Change | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a category | NONE | The URL should reflect the selected category | The URL is successfully reflecting the selected category | P3 | Works good | Pass
TC_CAT_08 | TS_005 | Verify Category Persistence | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a category 5)Refresh the page | NONE | The selected category should remain selected after the page refresh | The selected category remains selected after the page refresh | P3 | Works good | Pass
TC_CAT_09 | TS_005 | Verify Multiple Filters | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a category 5)Apply another filter such as price range | NONE | The products should be filtered based on both the selected category and the additional filter. | The products is filtered based on both the selected category and the additional filter. | P3 | Works good | Pass
TC_CAT_10 | TS_005 | Verify Filtered Product Count | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to the main product catalog page. 3)Check the Category filter dropdown. 4)Select a category | NONE | The product count displayed should match the number of products shown on the page. | The product count displayed is successfully matching the number of products shown on the page. | P4 | Works good | Pass

## Product page
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_PP_01 | TS_006 | Verify Product Information Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page | NONE | The product name, image, price, description, specifications, and availability should be displayed correctly. | The product name, image, price, description, specifications, and availability is displayed correctly. | P1 | Works good | Pass
TC_PP_02 | TS_006 | Verify Add to Cart Functionality | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Click on the "Add to cart" button | NONE | The specified quantity should be added to the shopping cart. | The specified quantity is added to the shopping cart. | P1 | Works good | Pass
TC_PP_03 | TS_006 | Verify Quantity Update | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Change the quantity to a different number 4)Click on the "Add to cart" button. | NONE | The specified quantity should be added to the shopping cart. | The specified quantity is added to the shopping cart. | P3 | Works good | Pass
TC_PP_04 | TS_006 | Verify Product Image Zoom | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Hover over the product image. | NONE | The product image should zoom in to show a larger view. | Whole we page will zoom. | P1 | Does not work | Failed
TC_PP_05 | TS_006 | Verify Product Reviews | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Scroll to the "Reviews" section. 4)Submit a new review. | NONE | Existing reviews should be displayed, and new reviews should be added successfully. | Existing reviews is displayed, and new reviews is added successfully. | P3 | Works good | Pass
TC_PP_06 | TS_006 | Verify Product Specifications | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Scroll to the "Specifications" section. | NONE | The product specifications should be displayed accurately. | The product specifications is displayed accurately. | P2 | Works good | Pass
TC_PP_07 | TS_006 | Verify Add to Wishlist Functionality | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Click on the "Add to wishlist" button. | NONE | The product should be added to the wishlist, and a confirmation message should be displayed. | The product isadded to the wishlist, and a confirmation message is displayed. | P2 | Works good | Pass
TC_PP_08 | TS_006 | Verify Related Products Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Scroll to the "Related products" section. | NONE | Related products should be displayed and clickable, leading to their respective product pages. | Related products is displayed and clickable, leading to their respective product pages. | P2 | Works good | Pass
TC_PP_09 | TS_006 | Verify Product Availability Message | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page | NONE | The availability status should be displayed clearly. | The availability status is displayed clearly. | P3 | Works good | Pass
TC_PP_10 | TS_006 | Verify Product Price Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page | NONE | The product price should be displayed accurately, showing any applicable discounts or promotions. | The product price is displayed accurately, showing any applicable discounts or promotions. | P3 | Works good | Pass

## Wishlist
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_WL_01 | TS_007 | Verify Adding Product to Wishlist | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Click on the "Add to wishlist" button. |  | The product should be added to the wishlist, and a confirmation message should be displayed. | The product is added to the wishlist, and a confirmation message should be displayed. | P1 | Works good | Pass
TC_WL_02 | TS_007 | Verify Wishlist Page Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website 2)Navigate to a product page 3)Add multiple products to the wishlist. 4)Navigate to the wishlist page. |  | All added products should be displayed with correct information | All added products is displayed with correct information | P1 | Works good | Pass
TC_WL_03 | TS_007 | Verify Removing Product from Wishlist | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the wishlist page. 3)Remove a product from the wishlist. |  | The product should be removed from the wishlist, and the page should update accordingly. | The product is removed from the wishlist, and the page is update accordingly. | P3 | Works good | Pass
TC_WL_04 | TS_007 | Verify Adding Wishlist Product to Cart | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the wishlist page. 3)Click "Add to cart" for a product. |  | The product should be added to the cart, and the cart count should increase. | The product is added to the cart, and the cart count is increase. | P1 | Works good | Pass
TC_WL_05 | TS_007 | Verify Wishlist Persistence after Logout | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the wishlist. 3)Log out. 4)Log back in. 5)Navigate to the wishlist page. |  | The wishlist should still contain the previously added products. | The wishlist is still containing the previously added products. | P3 | Works good | Pass
TC_WL_06 | TS_007 | Verify Clearing the Wishlist | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the wishlist. 3)Navigate to the wishlist page. 4)Use the "Clear wishlist" option. |  | All products should be removed from the wishlist, and the page should indicate an empty wishlist. | All products is removed from the wishlist, and the page indicates an empty wishlist. |  | Works good | Pass
TC_WL_07 | TS_007 | Verify Wishlist for Guest Users | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page as a guest user. 3)Click on the "Add to wishlist" button. |  | The site should prompt the user to log in or register. | The site is not prompting the user to log in or register. |  | Does not work | Failed
TC_WL_08 | TS_007 | Verify Maximum Wishlist Limit | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the wishlist until the maximum limit is reached. |  | Once the limit is reached, adding more products should prompt a message indicating the wishlist is full. | No limit is set, adding more products is not prompting a message indicating the wishlist is full. |  | Does not work | Failed
TC_WL_09 | TS_007 | Verify Product Quantity Update in Wishlist | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the wishlist page. 3)Update the quantity of a product. |  | The product quantity should update accordingly and reflect the changes. | The product quantity is updated accordingly and reflects the changes. |  | Works good | Pass
TC_WL_10 | TS_007 | Verify Wishlist Sharing Functionality | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the wishlist. 3)Use the "Email a friend" option. |  | The wishlist should be shared successfully via the selected method, and the recipient should receive a link or email. | The wishlist shares successfully via the selected method, and the recipient should receives a link or email. |  | Works good | Pass

## Shopping Cart
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_SC_01 | TS_008 | Verify Adding Product to Shopping Cart | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Click the "Add to cart" button. | NONE | The product should be added to the shopping cart, and a confirmation message should be displayed. | The product is added to the shopping cart, and a confirmation message is displayed. | P1 | Works good | Pass
TC_SC_02 | TS_008 | Verify Shopping Cart Page Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add multiple products to the shopping cart. 3)Navigate to the shopping cart page. | NONE | All added products should be displayed with correct information | All added products are displayed with correct information | P1 | Works good | Pass
TC_SC_03 | TS_008 | Verify Updating Product Quantity in Shopping Cart | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the shopping cart page. 3)Change the quantity of a product. 4)Click the "Update shopping cart" button. | NONE | The product quantity should update accordingly and the total price should reflect the change. | The product quantity is updated accordingly and the total price reflects the change. | P3 | Works good | Pass
TC_SC_04 | TS_008 | Verify Removing Product from Shopping Cart | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the shopping cart page. 3)Click the "Remove" button next to a product. | NONE | The product should be removed from the shopping cart, and the total price should update accordingly. | The product is removed from the shopping cart, and the total price is updated accordingly. | P1 | Works good | Pass
TC_SC_05 | TS_008 | Verify Shopping Cart Persistence after Logout | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the shopping cart. 3)Log out. 4)Log back in. 5)Navigate to the shopping cart page. | NONE | The shopping cart should still contain the previously added products. | The shopping cart is still containing the previously added products. | P3 | Works good | Pass
TC_SC_06 | TS_008 | Verify Clearing the Shopping Cart | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the shopping cart. 3)Navigate to the shopping cart page. 4)Use the "Clear shopping cart" option. | NONE | All products should be removed from the shopping cart, and the page should indicate an empty cart. | All products is removed from the shopping cart, and the page indicates an empty cart. |  | Works good | Pass
TC_SC_07 | TS_008 | Verify Applying Discount Code | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the shopping cart. 3)Navigate to the shopping cart page. 4)Enter a valid discount code. 5)Click the "Apply coupon" button. | NONE | The discount should be applied, and the total price should reflect the discount. | The discount is applied, and the total price reflects the discount. |  | Works good | Pass
TC_SC_08 | TS_008 | Verify Estimating Shipping Costs | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the shopping cart. 3)Navigate to the shopping cart page. 4)Enter a shipping location. 5)Click the "Estimate shipping" button. | NONE | The estimated shipping cost should be displayed based on the entered location. | The estimated shipping cost is displayed based on the entered location. |  | Works good | Pass
TC_SC_09 | TS_008 | Verify Proceeding to Checkout | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Add products to the shopping cart. 3)Navigate to the shopping cart page. 4)Click the "Proceed to checkout" button. | NONE | The user should be redirected to the checkout page to complete the purchase. | The user is redirected to the checkout page to complete the purchase. |  | Works good | Pass
TC_SC_10 | TS_008 | Verify Shopping Cart for Guest Users | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page as a guest user (not logged in). 3)Click the "Add to cart" button. 4)Navigate to the shopping cart page. 5)Click the "Proceed to checkout" button. | NONE | The guest user should be able to add products to the shopping cart and proceed to checkout, with options to log in or continue as a guest during the checkout process. | The guest user is able to add products to the shopping cart and proceed to checkout, with options to log in or continue as a guest during the checkout process. |  | Works good | Pass

## Change Password
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_CP_01 | TS_009 | Verify Change Password Page Access | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Log in to the website. 3)Navigate to the "My Account" section. 4)Click on "Change password".. | NONE | The Change Password page should be displayed. | The Change Password page is displayed. | P1 | Works good | Pass
TC_CP_02 | TS_009 | Verify Page Elements Display | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. | NONE | The page should display "Old password", "New password", "Confirm new password" fields, and a "Change password" button. | The page displays "New password", "Confirm new password" fields, and a "Change password" button. | P1 | Does not work | Fail
TC_CP_03 | TS_009 | Verify Change Password with Valid Data | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. 3)Enter the correct current password. 4)Enter a valid new password. 5)Confirm the new password. 6)Click the "Change password" button. | Password: shreyaK Password Confirm: shreyaK | The password should be changed successfully, and a confirmation message should be displayed. | The password is changed successfully, and a confirmation message is displayed. | P3 | Works good | Pass
TC_CP_04 | TS_009 | Verify Change Password with same password as before | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. 3)Enter an incorrect current password. 4)Enter a valid new password. 5)Confirm the new password. 6)Click the "Change password" button. | Password: shreyaK Password Confirm: shreyaK | An error message should be displayed indicating the same password as before | Your password has been successfully updated. | P1 | Works good | Fail
TC_CP_05 | TS_009 | Verify Change Password with Mismatched New Passwords | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. 3)Enter the correct current password. 4)Enter a new password. 5)Enter a different password in the confirmation field. 6)Click the "Change password" button. | Password: shreyaK Password Confirm: kshr | An error message should be displayed indicating the passwords do not match. | An error message is displayed indicating the passwords do not match. | P3 | Works good | Pass
TC_CP_06 | TS_009 | Verify Change Password with Weak New Password | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. 3)Enter the correct current password. 4)Enter a weak new password (e.g., "123"). 5)Confirm the new password. 6)Click the "Change password" button. | Password: aqaq Password Confirm: aqaq | An error message should be displayed indicating the new password is too weak. | An error message is displayed indicating the new password is too weak. | P2 | Works good | Pass
TC_CP_07 | TS_009 | Verify Change Password with Empty Fields | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. 3)Leave one or more fields empty. 4)Click the "Change password" button. | NONE | An error message should be displayed indicating that all fields are required. | An error message is displayed indicating that all fields are required. | P3 | Works good | Pass
TC_CP_08 | TS_009 | Verify Change Password Functionality for Logged-Out Users | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Log out of the website. 3)Try to navigate directly to the Change Password page URL. |  | The user should be redirected to the login page. | The user is redirected to the login page. | P3 | Works good | Pass
TC_CP_09 | TS_009 | Verify Password Change Persistence | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Change the password successfully. 3)Log out. 4)Log back in with the new password. |  | The user should be able to log in with the new password. | The user is be able to log in with the new password. | P3 | Works good | Pass
TC_CP_10 | TS_009 | Verify Password Complexity Requirements | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the Change Password page. 3)Enter the correct current password. 4)Enter a new password that doesn't meet complexity requirements (e.g., too short, no special characters). 5)Confirm the new password. 6)Click the "Change password" button. |  | An error message should be displayed indicating the password does not meet the complexity requirements. | An error message is displayed indicating the password does not meet the complexity requirements. | P2 | Works good | Pass

## Product review
Test case ID | Test Scenerio | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Comments | Status
TC_PR_01 | TS_0010 | Verify Access to Product Reviews Section | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Scroll down to the product reviews section. |  | The product reviews section should be displayed on the product page. | The product reviews section Is displayed on the product page. | P1 | Works good | Pass
TC_PR_02 | TS_0010 | Verify Submitting a Review with Valid Data | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Scroll down to the product reviews section. 4)Enter a valid title, review text, and rating. 5)Click the "Submit" button. |  | The review should be submitted successfully, and a confirmation message should be displayed. | The review is submitted successfully, and a confirmation message is displayed. | P1 | Works good | Pass
TC_PR_03 | TS_0010 | Verify Submitting a Review without Name | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Scroll down to the product reviews section. 4)Leave the title field empty, enter review text and rating. 5)Click the "Submit" button. |  | An error message should be displayed indicating that the title field is required. | An error message is displayed indicating that the title field is required. | P3 | Works good | Pass
TC_PR_04 | TS_0010 | Verify Submitting a Review without Text | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Scroll down to the product reviews section. 4)Enter a valid title and rating, leave the review text field empty. 5)Click the "Submit" button. |  | An error message should be displayed indicating that the review text field is required. | An error message is displayed indicating that Please select a review rating! | P1 | Works good | Pass
TC_PR_05 | TS_0010 | Verify Submitting a Review without Rating | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Scroll down to the product reviews section. 4)Enter a valid title and review text, leave the rating field empty. 5)Click the "Submit" button. |  | An error message should be displayed indicating that the rating field is required. | An error message is displayed indicating that the rating field is required. | P3 | Works good | Pass
TC_PR_06 | TS_0010 | Verify Display of Submitted Reviews | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Submit a review for a product. 3)Refresh the product page or navigate to the reviews section. |  | The submitted review should be displayed in the reviews section with the correct title, text, and rating. | The submitted review is displayed in the reviews section with the correct title, text, and rating. | P2 | Works good | Pass
TC_PR_07 | TS_0010 | Verify Review Sorting and Filtering | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to the product reviews section of a product page. 3)Use sorting and filtering options. |  | Reviews should be sorted and filtered according to the selected options. | Reviews is sorted and filtered according to the selected options. | P3 | Works good | Pass
TC_PR_08 | TS_0010 | Verify Review Length Validation | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page. 3)Scroll down to the product reviews section. 4)Enter a title, rating, and a review text that exceeds the maximum allowed length. 5)Click the "Submit" button. |  | An error message should be displayed indicating the review text exceeds the maximum length. | An error message is displayed indicating the review text exceeds the maximum length. | P3 | Works good | Pass
TC_PR_09 | TS_0010 | Verify Review Submission for Logged-Out Users | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Log out if logged in. 3)Navigate to a product page. 4)Scroll down to the product reviews section. 5)Try to submit a review. |  | The user should be prompted to log in or register before submitting a review. | Thank you for your review. It has been submitted to the webmaster for approval. | P3 | Works good | Fail
TC_PR_10 | TS_0010 | Verify Display of Average Rating | Open tutorialsninja in chrome browser | 1)Go to tutorialsninja website. 2)Navigate to a product page with multiple reviews. 3)Check the average rating displayed near the product title or in the reviews section. |  | The average rating should be correctly calculated and displayed based on the ratings of the submitted reviews. | The average rating should be correctly calculated and displayed based on the ratings of the submitted reviews. | P2 | Works good | Pass

## Bug Report
Bug ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshot
Bug ID__001 | Dropdown is not displayed when you hover on Tablets, Software, Phones& PDAs and Cameras. | 1)Open tutorialsninja 2)Locate the Dropdown Trigger 3)Attempt to Open the Dropdown 4)Observe the Behavior | Dropdown should be displayed when you hover on Tablets, Software, Phones& PDAs and Cameras. | Dropdown was not displayed | S3 | P2
Bug ID__002 | No option is being displayed for choosing state in availibility option | 1)Open tutorialsninja 2)Sign In 3)select one product 4)Check for options in availibility option section for choosing the state | Options should be displayed for choosing the state | There was no options for choosing the state | S3 | P2
Bug ID__003 | Repetitive of date and time field in product page | 1)Open tutorialsninja 2)Sign In 3)select one product 4)Check date and time options | Repetition of any input field should not be there | Date and Time fields are repetited two times current exchange rates. | S2 | P2
Bug ID__004 | review for a particular not working in product page | 1)Open tutorialsninja 2)Sign In 3)select one product 4)Check for the review | Star should be selected and review should be submitted for particular product | Review not submitted | S1 | P1
Bug ID__005 | In dropdown it shows product availibility 0 | 1)Open Nopcommerce 2)check on products | It should show the total product available | Not giving the exact to9tal available product numbers | S3 | P3
Bug ID_006 | slidshow of product images without zooming not available | 1)Open tutorialsninja 2)Go to the one product | Slideshow of the product images in websiite should be available | No function for slideshow without zooming | S2 | P1
Bug ID_007 | No forgot password option | 1)Open tutorialsninja 2)Go to the My Account | Forgot option should be there and the user should be able to log in successfully or receive a password reset email if the entered email address is valid and registered. | No forgot option | S2 | P1
Bug ID_008 | No Successful message displaying after submiting contact form | 1)Open tutorialsninja 2)Go to the contact | Successful message should be displayed after submiting the contact form successfully | No successful message displayed | S2 | P2
Bug ID_009 | Cannot proceed to add to cart without selecting state but there is no option for selecting state | 1)Open tutorialsninja 2)check on products | Should able to select state and proceed to add to cart | Cannot proceed to add to cart without selecting state but there is no option for selecting state | S3 | P2
Bug ID_010 | Proceed to checkout without login | 1)Open tutorialsninja 2)Go to the add to cart and proceed to checkout | Should redirected to login | Not redirecting to the login page | S3 | P3